## Dashboard
CortexKitchen Project Dashboard
Current milestone | P6-00 + per-node LLM cost attribution merged to main; Phase 6 in progress; next: P6-01 real data connectors
Last completed branch | dev -> main (P6-00 per-node model routing + cost attribution + screenshot reorg)
Current stable branches | main = P6-00 complete (per-node routing + cost); dev = P6-00 complete
Next recommended branch | P6-01 — Real data connectors
Phase | Status | % Complete | Key outcome
Phase 0 | Completed | 1 | Docs, roadmap, architecture, data model, APIs, evaluation, implementation plan
Phase 1 | Completed | 1 | API + Docker + DB + Seed + LLM + Core services + Qdrant complete+ langgraph skeleton + friday rush endpoint; dashboard complete; tests done
Phase 2 | Completed | 1 | Optimization layer: Prophet forecasting, inventory alerts, menu insights, and dashboard enhancementand evaluation refinement complete
Phase 3 | Completed | 1 | Advanced agentic features: auditable planning runs, richer critic evaluation, cost-aware scoring, and multi-scenario operational planning
Phase 4 | Completed | 1 | Productisation (no real data required): auth, LangSmith tracing, health checks, structured logging, LLM cost tracking, admin UI, runs UI, restaurant profiles, LLM provider swap, RAGAS evals, DeepEval, MCP server
Phase 5 | Completed | 1 | PDF/Excel export, frontend UX fixes, Redis cache, SSE streaming, what-if simulator, observability, evals, tenant isolation, email digest, RAG chatbot
Phase 6 | Planned | 0% | Real data connectors, async jobs, POS/reservations integrations, agentic loops, market intel, voice interface
Phase 7 | Planned | 0 | Production deploy: CI/CD, Railway/Fly.io, managed Postgres+Redis, production hardening, public release

## Phase Tracker
Phase | Order | Task ID | Workstream | Task | Detailed outcome / done means | Branch | Status | Priority | Owner | Start date | Target date | Done date | Progress % | Depends on | Tests expected | PR / Notes
Phase 0 | 1 | P0-01 | Repo | Create repo + branches | GitHub repo created, main/dev set up, no direct work on main | feature/phase0-repo-scaffold | Completed | High | Anoushka | 2026-03-15 | 2026-03-15 | 2026-03-15 | 1 |  | Smoke check repo + branch flow | Merged to dev, later synced to main
Phase 0 | 2 | P0-02 | Docs | PRD + roadmap + decisions | Core product direction locked in docs | feature/phase0-architecture-docs | Completed | High | Anoushka | 2026-03-15 | 2026-03-15 | 2026-03-15 | 1 | P0-01 | Doc review | Merged to dev, branch deleted
Phase 0 | 3 | P0-03 | Docs | Architecture doc | System layers, flow, LLM/RAG strategy captured | feature/phase0-architecture | Completed | High | Anoushka | 2026-03-15 | 2026-03-15 | 2026-03-15 | 100% | P0-02 | Doc review | Merged to dev, branch deleted
Phase 0 | 4 | P0-04 | Docs | Agents + data model + APIs | Agent specs, DB model, API contracts documented | feature/phase0-agents-data-api | Completed | High | Anoushka | 2026-03-15 | 2026-03-15 | 2026-03-15 | 100% | P0-03 | Doc review | Merged to dev, branch deleted
Phase 0 | 5 | P0-05 | Docs | Evaluation + implementation plan | Evaluation rubric and build order finalized | feature/phase0-evaluation-plan | Completed | High | Anoushka | 2026-03-15 | 2026-03-16 | 2026-03-16 | 100% | P0-04 | Doc review | Merged to dev, branch deleted
Phase 1 | 7 | P1-01 | Backend | API scaffold | FastAPI app boots, settings, health endpoints, dependency checks, tests pass | feature/phase1-api-scaffold | Completed | High | Anoushka | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | P0-06 | 3 unit tests + manual endpoint verification | Root, docs, /health, /health/dependencies verified
Phase 1 | 8 | P1-02 | Infra | Docker infra | docker-compose for Postgres, Qdrant, Redis; startup verified | feature/phase1-infra-docker | Completed | High | Anoushka | 2026-03-21 | 2026-03-21 | 2026-03-21 | 1 | P1-01 | Service startup smoke tests | Merged to dev, branch deleted
Phase 1 | 9 | P1-03 | Backend | DB schema + models | Initial relational schema for reservations, orders, complaints, traces | feature/phase1-db-schema | Completed | High | Anoushka | 2026-03-21 | 2026-03-21 | 2026-03-21 | 100% | P1-02 | Schema tests / migrations sanity | Merged to dev, branch deleted
Phase 1 | 10 | P1-04 | Data | Seed data | Pizza-heavy synthetic data with Friday spikes and simulated reservation/review sources | feature/phase1-seed-data | Completed | High | Anoushka | 2026-04-04 | 2026-04-04 | 2026-04-04 | 100% | P1-03 | Seed script smoke tests | Merged to dev, branch deleted
Phase 1 | 11 | P1-05 | Backend | LLM provider layer | Base provider + Gemini provider , Groq Provider + prompt utilities | feature/phase1-llm-provider | Completed | High | Anoushka | 2026-04-04 | 2026-04-04 | 2026-04-04 | 100% | P1-01 | Provider unit/integration tests | Merged to dev, branch deleted
Phase 1 | 12 | P1-06 | Backend | Core services | Reservation analytics, baseline forecast, complaint summary, critic rules | feature/phase1-core-services | Completed | High | Anoushka | 2026-04-04 | 2026-04-04 | 2026-04-04 | 100% | P1-03 | Unit tests for services/rules | Merged to dev, branch deleted
Phase 1 | 13 | P1-07 | Memory | Qdrant memory | Collections, embeddings, retrieval helpers for complaints/SOPs | feature/phase1-qdrant-memory | Completed | Medium | Anoushka | 2026-04-05 | 2026-04-05 | 2026-04-05 | 100% | P1-02, P1-05 | Integration tests with retrieval | Merged to dev, branch deleted
Phase 1 | 14 | P1-08 | Agents | LangGraph skeleton | Shared state, nodes, graph edges, stub flow | feature/phase1-langgraph-skeleton | Completed | High | Anoushka | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | P1-05, P1-06 | Graph flow tests | Merged to dev, branch deleted
Phase 1 | 15 | P1-09 | Backend | Friday rush endpoint | End-to-end planning endpoint + aggregated recommendation + trace write | feature/phase1-friday-rush-endpoint | Completed | High | Anoushka | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | P1-06, P1-07, P1-08 | Integration + manual demo test | Merged to dev, branch deleted
Phase 1 | 16 | P1-10 | Frontend | Dashboard MVP | Planning result UI with forecast, complaint, critic, trace sections | feature/phase1-dashboard | Completed | Medium | Anoushka | 2026-04-10 | 2026-04-11 | 2026-04-11 | 100% | P1-09 | Frontend smoke tests | Merged to dev, branch deleted
Phase 1 | 17 | P1-11 | Quality | Phase 1 tests | Unit + integration + first E2E Friday rush flow | feature/phase1-tests | Completed | High | Anoushka | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | P1-09, P1-10 | Pytest + scenario checklist | Merged to dev, branch deleted
Phase 1 | 18 | P1-12 | Release | Sync Phase 1 to main | Stable MVP milestone on main | dev -> main PR | Completed | High | Anoushka | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | P1-11 | Milestone verification | Main synced
Phase 2 | 19 | P2-01 | Forecasting | Prophet upgrade | Replace/add baseline with Prophet forecasting path | feature/phase2-prophet-upgrade | Completed | Medium | Anoushka | 2026-04-16 | 2026-04-17 | 2026-04-19 | 100% | P1-12 | Forecast comparison tests | Merged to dev, branch deleted
Phase 2 | 20 | P2-02 | Ops | Inventory alerts | Shortage/overstock alerts using forecast + stock levels | feature/phase2-inventory-alerts | Completed | Medium | Anoushka | 2026-04-19 | 2026-04-19 | 2026-04-20 | 1 | P2-01 | Rule tests | Merged to dev, branch deleted
Phase 2 | 21 | P2-03 | Menu | Menu insights | Top/weak items and promo suggestions surfaced in API/UI | feature/phase2-menu-insights | Completed | Medium | Anoushka | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% | P1-12 | Menu service, node, graph, and e2e tests passed | Merged to dev, branch deleted
Phase 2 | 22 | P2-04 | Frontend | Dashboard enhancement | Product-grade dashboard with stronger layout hierarchy, dedicated agent panels, top summary KPIs, clearer operational sections, and drill-down-ready UI | feature/phase2-dashboard-enhancement | Completed | High | Anoushka | 2026-04-21 | 2026-04-22 | 2026-04-26 | 100% | P2-02, P2-03 | Frontend checks + UI walkthrough + dashboard smoke tests | Merged to dev, branch deleted , (force-with-lease)
Phase 2 | 23 | P2-05 | Quality | Evaluation refinement | Manual rubric + scenario checklist + automated sanity checks (schema validation, quantity realism, 24h feasibility) + critic calibration notes | feature/phase2-evaluation-refinement | Completed | High | Anoushka | 2026-04-26 | 2026-04-26 | 2026-04-26 | 100% | P2-01, P2-02, P2-03, P2-04 | Eval checks + scenario validation + rubric doc | Merged to dev, branch deleted
Phase 2 | 24 | P2-06 | Release | Sync Phase 2 to main | Phase 2 milestone verified on main (forecast + inventory + menu + dashboard + evaluation); release verification + notes | dev -> main PR | Completed | Medium | Anoushka | 2026-04-26 | 2026-04-26 | 2026-04-26 | 100% | P2-05 | Milestone verification checklist | Main synced
Phase 3 | 25 | P3-01 | Product | Runs & audit UI | Run history persisted in Postgres; runs list + drilldown page showing agent outputs, critic score, rag context, trace/audit ids | feature/phase3-runs-audit-ui | Completed | Medium | Anoushka | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% | P2-06 | API contract tests + UI smoke tests + trace retrieval tests | Merged to dev, branch deleted
Phase 3 | 26 | P3-02 | Quality | Advanced critic | Richer scoring dimensions + clearer revision reasons + actionable critic feedback for weak recommendations | feature/phase3-advanced-critic | Completed | Medium | Anoushka | 2026-04-27 | 2026-04-27 | 2026-04-27 | 1 | P3-01 | Critic tests + scenario review + regression checks | Merged to dev, branch deleted
Phase 3 | 27 | P3-03 | Scoring | Cost-aware scoring | Recommendation scoring with operational cost/benefit awareness (prep burden, stock risk, feasibility tradeoffs) | feature/phase3-cost-aware-scoring | Completed | Medium | Anoushka | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% | P3-02 | Rule tests + scoring checks + e2e scenario tests | Merged to dev, branch deleted
Phase 3 | 28 | P3-04 | Product | Scenario expansion | Extend beyond Friday Rush (weekday/weekend, holiday spike, low-stock weekend); reusable workflow framing + UI selection | feature/phase3-scenario-expansion | Completed | Medium | Anoushka | 2026-04-28 | 2026-04-29 | 2026-04-29 | 100% | P3-03 | Scenario tests + e2e flow tests + UI smoke tests | Merged to dev, branch deleted
Phase 3 | 29 | P3-05 | Release | Sync Phase 3 to main | Advanced milestone stabilized on main | dev -> main PR | Completed | Low | Anoushka | 2026-04-29 | 2026-04-29 | 2026-04-29 | 100% | P3-04 | Milestone verification checklist + demo run checklist | Main synced
Demo prep | 30 | PD-01 | Data | Seed data | Additional Seed Data for demo and minor ui polish | chore/seed-data | Completed | Low | Anoushka | 2026-05-16 | 2026-05-16 | 2026-05-16 | 100% | NONE | Seeded Data successfully | Merged to dev, branch deleted
Demo prep | 31 | PD-02 | Frontend | minor ui polish | minor ui polish | feat/demo-prep | Completed | Low | Anoushka | 2026-05-16 | 2026-05-16 | 2026-05-16 | 1 | NONE | Ui polish pass | Merged to dev, branch deleted
Demo prep | 31 | PD-03 | Frontend | loading state improvements | minor ui polish | feat/quick-fix | Completed | Low | Anoushka | 2026-05-19 | 2026-05-19 | 2026-05-19 | 100% | NONE | Ui polish pass | Merged to dev, branch deleted
Phase 4 | 1 | P4-01 | Product | Multi-tenant + auth | Users/orgs, login, workspace separation, role-based access, protected pages | feature/phase4-auth-multitenant | Completed | High | Anoushka | 2026-05-31 | 2026-05-31 | 2026-05-31 | 100% | P3-05 | Auth tests + access-control tests + UI smoke tests | Merged to dev, branch deleted
Phase 4 | 2 | P4-02 | Observability | LangSmith tracing | Enable LangSmith trace capture for all LangGraph nodes — set LANGCHAIN_TRACING_V2 + API key; verify per-node traces visible in LangSmith UI | feature/phase4-langsmith-tracing | Completed | High | Anoushka | 2026-05-31 | 2026-05-31 | 2026-05-31 | 1 | P3-05 | Trace visibility smoke test — confirm node names, LLM calls, latency appear in LangSmith dashboard | Merged to dev, branch deleted
Phase 4 | 3 | P4-03 | Infra | Real dependency health checks | Replace stub URL-existence checks in dependency_health.py with actual pings: psycopg2.connect(), QdrantClient.get_collections(), redis.ping(); return latency_ms and error detail per dependency | feature/phase4-health-checks | Completed | High | Anoushka | 2026-05-31 | 2026-05-31 | 2026-05-31 | 100% | P3-05 | Health check integration tests — confirm each service returns ok=True when running, ok=False when stopped | Merged to dev, branch deleted
Phase 4 | 4 | P4-04 | Observability | Structured logging (structlog) | Replace default FastAPI logging with structlog JSON output: run_id, node, duration_ms on every event; add request middleware for HTTP access logs | feature/phase4-structlog | Completed | Medium | Anoushka | 2026-05-31 | 2026-05-31 | 2026-05-31 | 100% | P4-02 | Log output unit tests — verify JSON fields present; smoke test that run_id propagates through nodes | Merged to dev, branch deleted
Phase 4 | 5 | P4-05 | Observability | Node latency + LLM cost tracking | Record started_at/ended_at/duration_ms per node in execution_trace (always-on, not debug-only); add prompt_tokens, completion_tokens, cost_usd per LLM call using Gemini usage API; store in planning_runs.meta (jsonb) | feature/phase4-cost-latency | Completed | Medium | Anoushka | 2026-05-31 | 2026-05-31 | 2026-05-31 | 100% | P4-04 | Cost tracking unit tests — verify token fields populated; integration test checks meta column written after run | Merged to dev, branch deleted
Phase 4 | 6 | P4-06 | Product | Admin + settings | Scenario templates, thresholds, capacity, menu/inventory settings, tenant config UI | feature/phase4-admin-settings | Completed | Medium | Anoushka | 2026-05-31 | 2026-05-31 | 2026-05-31 | 100% | P4-01 | UI smoke tests + settings persistence tests | Merged to dev, branch deleted
Phase 4 | 7 | P4-07 | Product | Runs UI — filter + diff view | Add scenario filter, date range picker, and critic score trend chart to /runs page; add side-by-side diff modal comparing critic dimension scores between two selected runs | feature/phase4-runs-diff-ui | Completed | Medium | Anoushka | 2026-05-31 | 2026-05-31 | 2026-05-31 | 100% | P4-01 | Frontend smoke tests + API filter parameter tests | Merged to dev, branch deleted
Phase 4 | 8 | P4-08 | Product | Configurable restaurant profiles | Add restaurant_profiles table (name, cuisine, capacity, peak_hours, timezone); planning run accepts restaurant_id; scenarios pull context from profile instead of hardcoded pizza assumptions; one Alembic migration | feature/phase4-restaurant-profiles | Completed | Medium | Anoushka | 2026-05-31 | 2026-05-31 | 2026-05-31 | 1 | P4-06 | Migration smoke test + service unit tests + scenario context injection tests | Merged to dev, branch deleted
Phase 4 | 9 | P4-09 | Infra | LLM provider hot-swap + fallback | LLM_PROVIDER env var selects active provider (gemini¦groq); if primary fails mid-run, automatically retry with fallback provider; log provider used per run in structlog and LangSmith metadata | feature/phase4-llm-providers | Completed | Low | Anoushka | 2026-06-01 | 2026-06-01 | 2026-06-01 | 1 | P4-02 | Provider unit tests — verify complete() and complete_json() work for new providers; integration test with one full planning run per provider | Merged to dev, branch deleted
Phase 4 | 10 | P4-10 | Quality | RAGAS eval for complaint RAG pipeline | Integrate ragas to evaluate complaint_intelligence node: faithfulness, answer relevancy, context precision/recall scored against Qdrant retrieval; run as part of eval suite with LangSmith dataset | feature/phase4-ragas-evals | Completed | Low | Anoushka | 2026-06-01 | 2026-06-01 | 2026-06-01 | 1 | P4-02 | RAGAS metric thresholds pass (faithfulness > 0.8); eval script runs without error in CI | Merged to dev, branch deleted
Phase 4 | 11 | P4-11 | Quality | DeepEval LLM output quality tests | Add deepeval metrics to pytest suite: HallucinationMetric on critic output, AnswerRelevancyMetric on agent recommendations; gate CI — fail if quality drops below threshold | feature/phase4-deepeval | Completed | Low | Anoushka | 2026-06-03 | 2026-06-03 | 2026-06-03 | 1 | P4-10 | DeepEval tests pass in pytest; CI pipeline fails on hallucination score above threshold | Merged to dev, branch deleted
Phase 4 | 12 | P4-12 | Infra | MCP server — expose planning API | Wrap POST /planning/run and GET /runs as MCP tools using Anthropic Python MCP SDK; expose run_planning_scenario tool and get_run_history resource; test with Claude Desktop | feature/phase4-mcp-server | Completed | Low | Anoushka | 2026-06-03 | 2026-06-03 | 2026-06-03 | 1 | P4-01 | MCP tool smoke test — confirm Claude Desktop can trigger a planning run and retrieve run history | Merged to dev, branch deleted
Phase 4 | 13 | P4-13 | Release | Sync Phase 4 to main | Phase 4 milestone verified on main: auth, observability, evals, Redis cache, MCP server all stable. README updated. Demo run clean across all 4 scenarios. | dev -> main PR | Completed | Low | Anoushka | 2026-06-03 | 2026-06-03 | 2026-06-03 | 1 | P4-12 | Milestone verification checklist + demo run checklist + all Phase 4 integration tests green | Merged to main via dev PR
Phase 5 | 1 | P5-01 | Product | PDF export — manager summary | GET /runs/{id}/export?format=pdf — one-page summary with critic score, action items, forecast; WeasyPrint or reportlab; downloadable from runs page | feature/phase5-pdf-export | Completed | High | Anoushka |  |  |  | 0 | P4-13 | PDF generation unit test — all sections present; download endpoint smoke test | No blockers — quick win, strong demo artifact
Phase 5 | 2 | P5-02 | Product | Excel export — role-aware | GET /runs/{id}/export?format=xlsx — inventory + staffing sheet for chef, cost breakdown for owner; formatted with openpyxl; separate sheets per role | feature/phase5-excel-export | Completed | High | Anoushka |  |  |  | 0 | P5-01 | Excel generation unit test — verify sheets and headers; download endpoint smoke test | Pairs with P5-01
Phase 5 | 3 | P5-03 | Product | Frontend UX fixes | Fix /data-health 404 (page missing, NavBar links to it); add restaurant profile selector to dashboard run form; add export download buttons to runs page; add input validation to settings page; surface cost/token aggregate on runs list | feature/phase5-frontend-ux | Completed | High | Anoushka |  |  |  | 0 | P5-01 | Smoke tests: data-health loads; profile selector sends restaurant_id; settings rejects invalid range | Fixes live 404 bug. Frontend-only — no API changes needed
Phase 5 | 4 | P5-04 | Infra | Redis caching for planning runs | Cache planning run results by scenario+date key (TTL 1hr) using aioredis; skip full graph on cache hit; add cache_hit flag to response; Redis already in docker-compose | feature/phase5-redis-cache | Completed | Medium | Anoushka |  |  |  | 0 | P4-13 | Cache unit tests — hit/miss logic; integration test: second identical run returns faster with cache_hit=True | Redis already running — no infra change needed
Phase 5 | 5 | P5-05 | Infra | SSE streaming — node-by-node results | Stream planning run results node-by-node to frontend via Server-Sent Events; frontend renders each agent card as its node completes; reduces perceived latency significantly | feature/phase5-streaming | Completed | Medium | Anoushka |  |  |  | 0 | P5-04 | SSE endpoint smoke test — events emitted per node; frontend confirms cards render progressively | No async queue needed — SSE works on sync runs
Phase 5 | 6 | P5-06 | Product | What-if simulator | Sliders for covers/date/scenario in UI — re-run only forecast + cost nodes via partial LangGraph execution — instant updated output without full planning run | feature/phase5-whatif-simulator | Completed | Medium | Anoushka |  |  |  | 0 | P4-08 | Partial graph execution unit test; UI slider integration test; output diff from full run test | No blockers — works with synthetic data, strong interactive demo
Phase 5 | 7 | P5-07 | Observability | OpenTelemetry + Prometheus metrics | Add opentelemetry-instrumentation-fastapi + prometheus-fastapi-instrumentator; expose /metrics endpoint; capture HTTP request latency, throughput, error rate; Grafana dashboard | feature/phase5-opentelemetry | Completed | Medium | Anoushka |  |  |  | 0 | P4-05 | Prometheus scrape test — /metrics returns valid prom format; Grafana panels show data | Pure infra — no data dependency
Phase 5 | 8 | P5-08 | Infra | Sentry error tracking | Add sentry-sdk[fastapi]; capture unhandled exceptions, slow transactions, LangGraph node errors; verify error appears in Sentry on intentional 500 | feature/phase5-sentry | Completed | Low | Anoushka |  |  |  | 0 | P4-05 | Sentry capture smoke test — intentional exception appears within 30s | Quick win — ~1 day effort
Phase 5 | 9 | P5-09 | Quality | LangSmith dataset + regression evals | Build golden dataset from best historical planning runs already in DB; run automated evaluators (critic score > 3.5, plan contains restock recommendation); fail CI on regression | feature/phase5-langsmith-evals | Completed | Medium | Anoushka |  |  |  | 0 | P4-02 | Eval pass rate > 90% on golden dataset; CI fails on intentional prompt regression | We already have runs in the DB — use those as golden dataset
Phase 5 | 10 | P5-10 | Product | Multi-tenant workspace isolation | Full tenant isolation: Postgres row-level security per org; Qdrant shared collection with restaurant_id + doc_type payload filters (NOT per-tenant collections — see D-009); no data bleed between orgs | feature/phase5-tenant-isolation | Completed | High | Anoushka |  |  |  | 0 | P4-01 | Tenant isolation tests — verify org A cannot read org B runs; Qdrant filter tests | Auth done in P4-01. Qdrant: payload pre-filter only, not per-tenant collections
Phase 5 | 11 | P5-11 | Product | Weekly digest email | Auto-generated Sunday summary + Monday recommendations via APScheduler; formatted email via SendGrid/Resend; per-restaurant scheduling; PDF attached | feature/phase5-weekly-digest | Completed | Medium | Anoushka |  |  |  | 0 | P5-01 | Scheduler unit test; email template render test; send smoke test with test API key | Works with synthetic data — auth and PDF export must be done first
Phase 5 | 12 | P5-12 | Product | RAG chatbot over run history | Conversational interface: answer questions like why did critic score drop last Friday — retrieves relevant runs + complaints from Postgres + Qdrant, streams reply via SSE; multi-turn memory | feature/phase5-rag-chatbot | Completed | High | Anoushka |  |  |  | 0 | P5-05 | Retrieval unit test; multi-turn memory test; SSE streaming smoke test; hallucination check via DeepEval | SSE must be done first (P5-05). Works with synthetic run history
Phase 5 | 13 | P5-13 | Release | Sync Phase 5 to main | Phase 5 milestone verified: PDF/Excel export, SSE streaming, Redis cache, tenant isolation all stable. README and docs updated. | dev -> main PR | Completed | Low | Anoushka |  |  |  | 0 | P5-12 | Milestone checklist + demo run with all Phase 5 features active | Update docs after merge
Phase 6 | 0 | P6-00 | Infra | Per-node model tier routing via CometAPI | CometProvider (AsyncOpenAI), 3-tier registry (fast/balanced/strong), llm_registry in OrchestratorState, node-level tier overrides, cost tracking across all tiers. LangSmith verified per-node model assignment. Async fix cut fan-out from 48.7s to 17s. | feature/per-node-model-routing | Completed | High | anoushka | 2026-06-19 | 2026-06-19 | 2026-06-19 | 100 |  | No | Merged to dev 2026-06-19. PR: feat: per-node model tier routing via CometAPI
Phase 6 | 1 | P6-01 | Integrations | Real data connectors — framework | CSV/POS import framework; first connector (Square/Toast CSV); map to existing orders schema; replace synthetic seed with real import path; validate against InventoryService and ForecastService | feature/phase6-data-connectors | Planned | High | Anoushka |  |  |  | 0 | P5-13 | Connector smoke tests + data validation + import e2e | Requires real restaurant data — foundational for all P6 tasks
Phase 6 | 2 | P6-02 | Infra | Async jobs + Redis queue | Async planning runs via Redis job queue; job status endpoint; retries; dedupe by scenario+date; non-blocking HTTP | feature/phase6-async-redis | Planned | Medium | Anoushka |  |  |  | 0 | P6-01 | Queue tests + retry tests + load smoke tests | Makes sense once runs take time with real data
Phase 6 | 3 | P6-03 | Integrations | POS connector — Square/Toast CSV | Import orders from Square/Toast CSV export; validate against InventoryService and ForecastService; replace synthetic order seed with real import path | feature/phase6-pos-connector | Planned | High | Anoushka |  |  |  | 0 | P6-01 | CSV import unit tests + ForecastService integration test with imported data
Phase 6 | 4 | P6-04 | Integrations | Reservations connector — Resy/OpenTable | OAuth2 flow + webhook ingestion for Resy or OpenTable; map to reservations schema; sync on webhook event; add connector health status to /health/dependencies | feature/phase6-reservations-connector | Planned | Medium | Anoushka |  |  |  | 0 | P6-03 | OAuth smoke test + webhook ingestion test + schema mapping validation
Phase 6 | 5 | P6-05 | Agents | Agentic loops — ReAct node | Optional ReAct-style node: LLM decides tool call, observe result, re-call if needed; use for inventory verification against live POS; bounded loop max 3 iterations | feature/phase6-react-node | Planned | Medium | Anoushka |  |  |  | 0 | P6-03 | ReAct loop unit tests — verify max iteration cap; integration test with deliberately bad inventory | Needs live POS data to be meaningful
Phase 6 | 6 | P6-06 | Product | Market intelligence panel | Google Trends API + NewsAPI + food subreddits — new market_intelligence_node — trend signals fed into planning run and surfaced in dashboard | feature/phase6-market-intelligence | Planned | Medium | Anoushka |  |  |  | 0 | P5-06 | Node integration test; dashboard smoke test | Requires external API keys (Google Trends, NewsAPI)
Phase 6 | 7 | P6-07 | Product | Competitor monitor | Scrape nearby Zomato/Swiggy listings weekly via BeautifulSoup/Playwright; flag when competitor adds dish matching weak performers; store snapshots in Postgres | feature/phase6-competitor-monitor | Planned | Low | Anoushka |  |  |  | 0 | P6-06 | Scraper unit test + diff detection test + dashboard smoke test | Needs live scraping of competitor listings
Phase 6 | 8 | P6-08 | Product | Voice interface (Whisper) | Whisper transcription on recorded question — RAG chatbot answers — TTS reads back; manager asks questions while walking the floor; browser MediaRecorder API | feature/phase6-voice-interface | Planned | Low | Anoushka |  |  |  | 0 | P5-12 | Transcription accuracy smoke test; end-to-end voice-to-answer integration test | Blocked on RAG chatbot (P5-12)
Phase 6 | 9 | P6-09 | Release | Sync Phase 6 to main | Phase 6 milestone verified: POS connector, at least one real data import verified end-to-end. | dev -> main PR | Planned | Low | Anoushka |  |  |  | 0 | P6-08 | Milestone checklist + E2E smoke test with imported CSV data
Phase 7 | 1 | P7-01 | Release | CI/CD pipeline — GitHub Actions | Automated test suite on every PR (unit + integration + evals); lint; type check; build check on frontend; coverage report | feature/phase7-cicd | Planned | High | Anoushka |  |  |  | 0 | P6-09 | CI passes on clean repo; fails on intentional test break
Phase 7 | 2 | P7-02 | Release | Cloud deployment — Railway/Fly.io | Containerise API + frontend; deploy to Railway or Fly.io; configure managed Postgres + Redis + Qdrant; set production env vars | feature/phase7-cloud-deploy | Planned | High | Anoushka |  |  |  | 0 | P7-01 | Smoke test on production URL; health endpoint returns ok
Phase 7 | 3 | P7-03 | Release | Production hardening | Rate limiting (slowapi); secrets management; CORS lockdown; JWT key rotation; Sentry alerts for production errors | feature/phase7-prod-hardening | Planned | Medium | Anoushka |  |  |  | 0 | P7-02 | Rate limit smoke test; CORS rejection test; Sentry alert fires on 500
Phase 7 | 4 | P7-04 | Release | Sync Phase 7 to main — public release | Live production URL. README updated with live demo link. Portfolio-ready. | dev -> main PR | Planned | Low | Anoushka |  |  |  | 0 | P7-03 | Full E2E smoke test on production URL | Apply to jobs immediately after this merges. Update both docs.

## Git Practices
Git / Branching Rules
Branch | Purpose | Rule | Current note
main | Stable milestone only | Only sync from dev when a phase milestone is safe/demo-ready | Phase 3 already synced
dev | Active integration branch | All merged feature work lands here first | Current working base
feature/... | All implementation and docs work | Create from latest dev, PR back to dev, then delete branch | Current style
Local cleanup | After merge | Delete remote + local feature branch, checkout dev, pull latest | Continue throughout project